## Dashboard
Book Library Management — Project Tracker
AI-SDLC build process · product → modules → features → packets · updated live
Progress at a glance
Stage | Total | Done | In progress | Blocked | % Done
Product docs (24)
Packets — BRD
Packets — DESIGN
Packets — BUILD prompt
Packets — Execution
Packets — ENG-QA prompt
Packets — Evidence (gate)
Legend
Done | Authored / executed / gate green — depending on the stage.
In progress | Started but not yet meeting the stage's done definition.
Blocked | Cannot proceed — see linked Open Question or note in the row.
Not started | Nothing written or executed yet.
How to use
1. Update Status cells on the Product Docs and Packets sheets — KPI cards roll up automatically.
2. Acceptance Criteria sheet tracks per-AC verdicts captured by QA sessions; mark each as Pass / Fail once the packet's Evidence.md closes.
3. Open Questions: anything Blocker bounces the Status of dependent rows in other sheets.
4. Keep the Owner column current — it tells the next session who's accountable.
5. The Notes column on Packets is the spot for a one-line build/QA summary that the next session reads before resuming.
Resume on a new day
Read CLAUDE.md at the project root first. It lists current state, packet status, design tokens, run commands, and the next packet to execute. Last updated: 2026-06-29.

## Product Docs
Stage 1 · Product Planning Documents
24 docs across Discovery → Phase A–F. Status currently reflects what the agent has authored.
Phase | ID | File | Status | Owner | Last updated | Notes
Discovery | D0 | D0-BRD.md | Done | Builder | 2026-06-23 | Stack constraints updated to Postgres-only; frontend-skill note added.
Discovery | OQ | OQ-OPEN-QUESTIONS.md | Done | Builder | 2026-06-23 | OQ-002 resolved; OQ-001 still open.
Phase A | D1 | D1-ROADMAP.md | Done | Builder | 2026-06-23 | Two drops: walking skeleton + polish/deploy.
Phase A | D2 | D2-PRD.md | Done | Builder | 2026-06-23 | 5 user journeys.
Phase A | D15a | D15a-USER-STORIES-v1.md | Done | Builder | 2026-06-23 | 12 stories US-01..US-12.
Phase A | D5 | D5-ARCHITECTURE.md | Done | Builder | 2026-06-23 | Postgres + Alembic; folder layout updated.
Phase A | D5b | D5b-AI-READINESS.md | Done | Builder | 2026-06-23 | Composite 41/45 → AI-led.
Phase B | D3 | D3-FEATURE-CATALOG.md | Done | Builder | 2026-06-23 | 9 features mapped to packets.
Phase B | D10 | D10-QUALITY-NFRs.md | Done | Builder | 2026-06-23 | 10 NFRs, binary thresholds.
Phase B | D12 | D12-SECURITY.md | Done | Builder | 2026-06-23 | 10 threats, mitigations + backup note updated.
Phase C | D6 | D6-DATA-MODEL.md | Done | Builder | 2026-06-23 | Postgres-native DDL (BIGSERIAL, TIMESTAMPTZ, functional indexes).
Phase C | D7 | D7-API-CONTRACTS.md | Done | Builder | 2026-06-23 | OpenAPI 3.1, 5 endpoints, full schemas.
Phase C | D15b | D15b-USER-STORIES-v2.md | Done | Builder | 2026-06-23 | Build-precise ACs per US.
Phase C | D17 | D17-TEST-CASES.md | Done | Builder | 2026-06-23 | TC-001..TC-085 mapped to ACs and packets.
Phase D | D18 | D18-CLAUDE.md | Done | Builder | 2026-06-23 | Adds §0 Required Skills (FE skills mandatory for S-008..S-012).
Phase D | D8 | D8-BACKLOG.md | Done | Builder | 2026-06-23 | 13 stories → 13 packets.
Phase D | D4 | D4-ENFORCEMENT.md | Done | Builder | 2026-06-23 | Hooks + skills wired; CI Postgres service added.
Phase D | D9 | D9-DESIGN-SPEC.md | Done | Builder | 2026-06-23 | Includes skill preamble + per-page invocation checklist.
Phase E | D13 | D13-INFRA.md | Done | Builder | 2026-06-23 | Postgres in all envs; CI services block.
Phase E | D14 | D14-MIGRATION.md | Done | Builder | 2026-06-23 | Reframed as Postgres Alembic schema-evolution runbook.
Phase E | D11 | D11-TESTING.md | Done | Builder | 2026-06-23 | Postgres-backed transaction-per-test fixture (no SQLite).
Phase E | D16 | D16-FAULT-TOLERANCE.md | Done | Builder | 2026-06-23 | Postgres failure modes; SQLite entries removed.
Phase F | F4 | F4-OPERATING-MANUAL.md | Done | Builder | 2026-06-23 | Build vs. QA session modes.
Phase F | F3 | F3-HANDOVER.md | Done | Builder | 2026-06-23 | Per-session handover template.
Phase F | F1 | F1-LAUNCH.md | Done | Builder | 2026-06-23 | Launch prompt now mandates frontend-design + ui-ux-pro-max.
Phase F | F2 | F2-HANDOFF.md | Done | Builder | 2026-06-23 | QA-session boot prompt.

## Packets
Stage 2-3 · Packets (5-file cycle)
BRD · DESIGN · BUILD prompt authored up front. Execution → ENG-QA prompt → Evidence close the gate.
Packet | Module | Title | Depends on | BRD | DESIGN | BUILD prompt | Execution | ENG-QA prompt | Evidence | Branch | Owner | Notes
S-001 | database | Postgres + ORM + Alembic baseline | — | Done | Done | Done | Done | Done | Done | packet/S-001-postgres-orm-alembic | Builder | GREEN. All 7 ACs proven. Native Postgres 17 substitution recorded in Evidence.
S-002 | backend | FastAPI skeleton + DB session + CORS | S-001 | Done | Done | Done | Done | Done | Done | packet/S-002-fastapi-skeleton | Builder | GREEN. /healthz live + DB ping; CORS allow/deny verified.
S-003 | backend | POST /books | S-002 | Done | Done | Done | Done | Done | Done | packet/S-003-post-books | Builder | GREEN. Status canonicalization works ('read' -> 'Read').
S-004 | backend | GET /books, GET /books/{id} | S-003 | Done | Done | Done | Done | Done | Done | packet/S-004-get-books | Builder | GREEN. HARD_LIMIT=1000 (T-05); 6 tests + EXPLAIN ANALYZE on functional index.
S-005 | backend | PUT /books/{id} | S-004 | Done | Done | Done | Done | Done | Done | packet/S-005-put-books | Builder | GREEN. PUT preserves created_at by design (BookUpdate omits the field).
S-006 | backend | DELETE /books/{id} | S-005 | Done | Done | Done | Done | Done | Done | packet/S-006-delete-books | Builder | GREEN. 204 + empty body; psql confirms row gone.
S-007 | backend | Search + filter query params | S-006 | Done | Done | Done | Done | Done | Done | packet/S-007-search-filter | Builder | GREEN. Median latency 17.9 ms with 1000 rows (NFR Q-005 < 50 ms).
S-008 | frontend | Home page + frontend scaffolding | S-007 | Done | Done | Done | Done | Done | Done | packet/S-008-home-page | Builder | GREEN. frontend-design + ui-ux-pro-max committed tokens.js; spine-shelf hero.
S-009 | frontend | Books page (list + delete) | S-006,S-008 | Done | Done | Done | Done | Done | Done | packet/S-009-books-page | Builder | GREEN. BookCard mirrors home shelf color; ConfirmModal focus-trapped.
S-010 | frontend | AddBook page + shared BookForm | S-003,S-009 | Done | Done | Done | Done | Done | Done | packet/S-010-add-book-page | Builder | GREEN. Shared BookForm contract finalized. Two bugs found+fixed mid-cycle.
S-011 | frontend | EditBook page | S-005,S-010 | Done | Done | Done | Done | Done | Done | packet/S-011-edit-book-page | Builder | GREEN. FormSkeleton matches BookForm rhythm; BookForm untouched (SHA verified). 5 EditBook tests pass; 23 total. Build 79.28 KB gzip.
S-012 | frontend | Search + Filter UI | S-007,S-009 | Done | Done | Done | Done | Done | Done | packet/S-012-search-filter-ui | Builder | GREEN. 12 new Vitest tests (3 SearchBar + 3 FilterDropdown + 6 Books.filters); 35 total. ESLint clean. Build 80.74 KB gzip. URL is single source of truth for search/author/genre/status.
S-013 | infra | README + deploy + final gate | all | Done | Done | Done | Done | Done | Done | packet/S-013-readme-deploy | Builder | GREEN with deferrals. README + CI workflow + git init + initial commit (3dcb799). AC3 (live CI) and AC5 (clean-clone smoke on second machine) explicitly deferred per user direction; OQ-001 stays Open (deferred). All 6 ACs structurally met; see Evidence.md §Deferrals.

## Acceptance Criteria
Acceptance Criteria · per-packet binary checks
Each AC is binary (Pass / Fail). Verdicts populated by the QA session that authors Evidence.md.
Packet | AC | Description | Source (TC / US) | Verdict | Notes
S-001 | AC1 | docker compose up db boots Postgres on :5432 with named volume. | D6 | Pass
S-001 | AC2 | db_test service or db_test database available for tests. | D11 §2 | Pass
S-001 | AC3 | backend/models.py Book matches D6 exactly (columns, types, CHECK, indexes). | D6 §3 | Pass
S-001 | AC4 | database.py exposes engine, SessionLocal, get_db. | D5 §5 | Pass
S-001 | AC5 | alembic upgrade head materializes the books table per D6 §2. | D6 | Pass
S-001 | AC6 | alembic downgrade base then upgrade head is idempotent. | D14 | Pass
S-001 | AC7 | All four indexes from D6 present after upgrade head. | D6 §2 | Pass
S-002 | AC1 | uvicorn boots against live Postgres. | D5 | Pass
S-002 | AC2 | GET /docs → 200. | D7 | Pass
S-002 | AC3 | GET /openapi.json → 200 + valid JSON. | D7 | Pass
S-002 | AC4 | GET /healthz returns {status:ok, db:ok}; db field reflects SELECT 1. | D5 | Pass
S-002 | AC5 | CORS allows :5173, denies foreign origin. | D12 §T-07 | Pass
S-002 | AC6 | pytest runs against Postgres test DB with transaction-per-test rollback. | D11 §2 | Pass
S-002 | AC7 | ruff check backend → 0. | D18 | Pass
S-003 | AC1 | POST /books valid body → 201 + Book. | TC-001 / US-01 | Pass
S-003 | AC2 | Row persists in DB; id + created_at server-generated. | US-01 | Pass
S-003 | AC3 | Missing required field → 422. | TC-002 | Pass
S-003 | AC4 | status='Reading'→422; status='read'→201 normalized to 'Read'. | TC-003/004 | Pass
S-003 | AC5 | Length cap violations → 422. | TC-082 / T-06 | Pass
S-003 | AC6 | New row visible in subsequent reads. | US-01 AC5 | Pass
S-004 | AC1 | GET /books → Book[] ordered by created_at DESC. | TC-005/006 | Pass
S-004 | AC2 | Empty DB → []. | TC-005 | Pass
S-004 | AC3 | 1001 rows → response length 1000 (HARD_LIMIT). | TC-007 / T-05 | Pass
S-004 | AC4 | GET /books/{id} found → 200 + Book. | D7 §3.3 | Pass
S-004 | AC5 | Unknown id → 404 {detail: Book not found}. | TC-008 | Pass
S-004 | AC6 | Response strictly matches Book schema. | D7 §2 | Pass
S-005 | AC1 | PUT /books/{id} valid → 200 + updated Book. | TC-009 / US-03 | Pass
S-005 | AC2 | Row updates; created_at unchanged. | US-03 AC2 | Pass
S-005 | AC3 | Unknown id → 404. | US-03 AC3 | Pass
S-005 | AC4 | Extra field → 422. | TC-010 / T-04 | Pass
S-005 | AC5 | Validation rules match POST (status canonical, length caps). | D6 §5 | Pass
S-006 | AC1 | DELETE /books/{id} → 204, empty body. | TC-011 / US-04 | Pass
S-006 | AC2 | Row gone from DB. | US-04 AC2 | Pass
S-006 | AC3 | Unknown id → 404. | TC-012 | Pass
S-007 | AC1 | ?search=q case-insensitive substring on book_name or author. | TC-020/021 | Pass
S-007 | AC2 | Empty ?search behaves as no filter. | TC-022 | Pass
S-007 | AC3 | SQLi probe returns 0 rows; table intact. | TC-023 / T-01 | Pass
S-007 | AC4 | ?author=X exact case-insensitive. | TC-024 | Pass
S-007 | AC5 | ?genre=X exact case-insensitive. | TC-025 | Pass
S-007 | AC6 | ?status=Read filters to Read only. | TC-026 | Pass
S-007 | AC7 | ?status=foo → 422. | TC-027 | Pass
S-007 | AC8 | Filters compose with AND. | TC-028 | Pass
S-007 | AC9 | Median latency < 50 ms with 1000 rows. | TC-083 / Q-005 | Pass
S-008 | AC1 | Vite boots on :5173 with zero console errors. | D5 | Pass
S-008 | AC2 | Router covers /, /books, /add, /edit/:id. | D9 | Pass
S-008 | AC3 | services/api.js exposes axios instance + getBooks(). | D5 | Pass
S-008 | AC4 | Navbar present on every route with active link styling. | D9 §6 | Pass
S-008 | AC5 | Home renders Hero + Features + Stats. | D9 §2 | Pass
S-008 | AC6 | Stats reflect GET /books client-side. | US-09 | Pass
S-008 | AC7 | 0 books → 0 stats, no NaN. | US-10 AC2 | Pass
S-008 | AC8 | No horizontal scroll at 360 px. | Q-003 | Pass
S-008 | AC9 | Lint + smoke tests pass. | D11 | Pass
S-008 | AC10 | frontend-design + ui-ux-pro-max invoked; tokens.js committed. | D18 §0 | Pass | Mandatory.
S-009 | AC1 | Books page lists cards in 1/2/3 col grid. | D9 §3 | Pass
S-009 | AC2 | Empty state with Add CTA. | OQ-007 | Pass
S-009 | AC3 | Card shows title/author/genre/status + Edit/Delete. | D9 §6 | Pass
S-009 | AC4 | Delete confirm modal then removes card without reload. | TC-062 | Pass
S-009 | AC5 | Failed delete shows red toast; card stays. | Q-006 | Pass
S-009 | AC6 | Edit link navigates to /edit/:id. | D9 §5 | Pass
S-009 | AC7 | <script> in book_name renders as text. | TC-081 / T-02 | Pass
S-009 | AC8 | 360 px layout intact. | Q-003 | Pass
S-009 | AC9 | Lint + tests pass. | D11 | Pass
S-009 | AC10 | FE skills minuted; tokens extended. | D18 §0 | Pass | Mandatory.
S-010 | AC1 | Add page renders BookForm with 4 fields. | D9 §4 | Pass
S-010 | AC2 | Inline errors per field on empty submit. | US-12 AC1 | Pass
S-010 | AC3 | Status as radio (Read/Unread). | D9 §6 | Pass
S-010 | AC4 | Successful POST → toast + redirect to /books. | D9 §4 | Pass
S-010 | AC5 | API 422 maps to field-level errors. | US-12 AC2 | Pass
S-010 | AC6 | Form keyboard-navigable; Enter submits. | Q-002 | Pass
S-010 | AC7 | Submit disabled in-flight; no double-submit. | Q-006 | Pass
S-010 | AC8 | Lint + tests + 360 px clean. | D11 | Pass
S-010 | AC9 | FE skills invoked for form treatment. | D18 §0 | Pass | Mandatory.
S-011 | AC1 | Edit page prefills from GET /books/{id}. | US-03 AC5 | Pass
S-011 | AC2 | Skeleton placeholder while loading; no layout jump. | D9 §5 | Pass
S-011 | AC3 | PUT success → toast + redirect to /books. | D7 | Pass
S-011 | AC4 | 404 on load → redirect /books + error toast. | D16 | Pass
S-011 | AC5 | 422 on PUT → inline errors via shared plumbing. | US-12 AC2 | Pass
S-011 | AC6 | BookForm contract unchanged. | S-010 | Pass
S-011 | AC7 | Lint + tests + 360 px clean. | D11 | Pass
S-011 | AC8 | FE skills invoked for skeleton pattern. | D18 §0 | Pass | Mandatory.
S-012 | AC1 | Filter bar with SearchBar + 3 dropdowns. | D9 §3 | Pass | Books.filters.test.jsx — sticky filter bar test.
S-012 | AC2 | Search debounces 250ms then fetches. | TC-063 | Pass | Books.filters.test.jsx — composes search + dropdown params (250ms debounce).
S-012 | AC3 | Filters update URL params and refetch combined. | TC-064 | Pass | Books.filters.test.jsx — dropdown updates URL + refetches.
S-012 | AC4 | Author/Genre options derive from current results. | D9 §6 | Pass | Books.filters.test.jsx — populates Author/Genre sorted, Status fixed.
S-012 | AC5 | Clear-button resets search. | D9 §6 | Pass | Books.filters.test.jsx + SearchBar.test.jsx — clear button visibility + refetch.
S-012 | AC6 | Filters persist across navigation via URL. | D9 | Pass | Books.filters.test.jsx — mounts at /books?search=ato&status=Read; inputs reflect URL.
S-012 | AC7 | Lint + tests + 360 px clean. | D11 | Pass | npm test 35/35; npm run lint clean; flex/grid wraps at 360 px.
S-012 | AC8 | FE skills invoked for filter-bar styling. | D18 §0 | Pass | Mandatory. Skills invoked in prior authoring session — design choices recorded in Books.jsx lines 156-163.
S-013 | AC1 | README covers 5-minute local setup end-to-end. | D13 | Pass | README.md §Quickstart copy-pasteable; commands derived from the working tree that already produces 37+35 green tests.
S-013 | AC2 | .env.example files complete; no secret committed. | T-08 | Pass | backend/.env.example + frontend/.env.example complete; .env files not staged (git ls-files ¦ grep .env$ empty).
S-013 | AC3 | CI workflow with Postgres service container green on PR. | D4 §6 | Pass (structure) / deferred (live) | .github/workflows/ci.yml created per D4 §6; will run on first push to a GitHub remote (not yet pushed).
S-013 | AC4 | Deploy notes for Render + Vercel. | D13 | Pass | README §Deploy covers Render service config + Vercel project config; labelled illustrative because OQ-001 is deferred.
S-013 | AC5 | Clean-clone smoke under 5 min; recorded in Evidence. | Q-008 | Deferred | Per user direction (2026-06-29). To close: run README §Quickstart on a fresh machine with stopwatch + screenshot, append §AC5 Live Smoke block to Evidence.
S-013 | AC6 | git ls-files ¦ grep -E .env$ returns empty. | T-08 | Pass | Verified post-commit on 3dcb799: empty. Also verified .venv, node_modules, __pycache__, dist all unstaged.

## Open Questions
Open Questions
Blockers halt downstream packets. Resolve, then mirror the decision into the relevant doc.
ID | Question | Status | Affects | Decision / Resolution | Owner | Updated
OQ-001 | Production deploy target (Render+Vercel vs Railway vs Fly). | Open (deferred) | D13, S-013 | Deferred past S-013 close at user direction (2026-06-29). README §Deploy documents Render + Vercel illustratively. | Builder | 2026-06-29
OQ-002 | Database choice across environments. | Resolved | D5, D6, D11, D13, D14, D16 | PostgreSQL in dev/test/prod; docker-compose locally; managed in prod. No SQLite. | Builder | 2026-06-23
OQ-003 | genre free-text vs enum? | Resolved | D6, S-007, S-012 | Free-text in v1; UI dropdown populated from distinct values in current results. | Builder | 2026-06-23
OQ-004 | created_at format from API. | Resolved | D7 | UTC ISO 8601 from API; humanize client-side via Intl.RelativeTimeFormat. | Builder | 2026-06-23
OQ-005 | Client- or server-side stats? | Resolved | F-007, S-008 | Client-side from GET /books in v1; server endpoint when row count grows past 1k. | Builder | 2026-06-23
OQ-006 | Normalize status case on input? | Resolved | S-003, S-005 | Accept case-insensitive; persist canonical 'Read'/'Unread'. | Builder | 2026-06-23
OQ-007 | Books page empty state. | Resolved | S-009 | Centered empty-state card with 'Add your first book' CTA. | Builder | 2026-06-23

## User Stories
User Stories
Business-language US-01..US-12 with build-precise links to features and packets.
ID | Story | Features | Packets | Status | Notes
US-01 | Add a book to my library. | F-002, F-004 | S-003, S-010 | Done | S-003 + S-010 both green.
US-02 | See all my books on one page. | F-003 | S-004, S-009 | Done | S-004 + S-009 both green.
US-03 | Edit a book's details. | F-002, F-004 | S-005, S-011 | Done | S-005 + S-011 both green.
US-04 | Delete a book. | F-002, F-003 | S-006, S-009 | Done | S-006 + S-009 both green.
US-05 | Search by title or author. | F-005 | S-007, S-012 | Done | S-007 + S-012 both green.
US-06 | Filter by author. | F-006 | S-007, S-012 | Done | S-007 + S-012 both green.
US-07 | Filter by genre. | F-006 | S-007, S-012 | Done | S-007 + S-012 both green.
US-08 | Filter by reading status. | F-006 | S-007, S-012 | Done | S-007 + S-012 both green.
US-09 | See how many books / how many read. | F-007 | S-008 | Done | S-008 covers stats client-side.
US-10 | A friendly home page. | F-001 | S-008 | Done | S-008 hero + features + stats + CTAs.
US-11 | Use the app on my phone. | F-001..F-006 | S-008..S-012 (Q-003) | Done | S-008..S-012 honor Q-003 (responsive at 360 px) in tests.
US-12 | Inline form errors next to fields. | F-004 | S-010, S-011 | Done | S-010 inline errors with aria-describedby.